## KONU Functionalities
Module | Task | Sub Task | Status
NFR – Platform Requirements | NFR-01 Availability | Monitor launch-critical flows | Not Started
| NFR-01 Availability | Define incident ownership | Not Started
| NFR-02 Performance | Set performance budgets for search/detail/map | Not Started
|  | Measure in launch environment | Not Started
| NFR-03 Security | Authentication & authorization | Not Started
|  | Secrets management & audit logs | Not Started
|  | Vulnerability remediation as release gate | Not Started
| NFR-04 Privacy | Consent & data minimization | Not Started
|  | Role access | Not Started
|  | Deletion/retention rules | Not Started
| NFR-05 Observability | Logs/metrics for critical APIs, AI calls, pipelines | Not Started
|  | Logs/metrics for payments/service requests | Not Started
| NFR-06 Analytics | Instrument funnel: discovery → lead/service request → fulfilment | Not Started
| NFR-07 Accessibility | Readable contrast | Not Started
|  | Keyboard/focus behaviour | Not Started
|  | Semantic labelling | Not Started
| NFR-08 Scalability | Avoid single points of failure | Not Started
|  | Document expected load assumptions | Not Started
A – Core Listings, Search & Property Detail | CL-01 Search & filters | Filter by location, type, price, core attributes | Not Started
| CL-01 Search & filters | Preserve selected filters | Not Started
| CL-02 Property card/detail | Show standardized core facts | Not Started
|  | Show last-updated & verification badge | Not Started
|  | Never show missing data as verified | Not Started
| CL-03 Map/list sync | Sync selection/filter between views | Not Started
|  | Keep property counts consistent (except clustering) | Not Started
| CL-04 Save/favorite | Save property to account | Not Started
|  | Remove saved property | Not Started
|  | Persist after login | Not Started
| CL-05 Lead/service CTA | Route enquiry to CRM/ops | Not Started
|  | Capture source, property/project ID, contact/consent, timestamp, campaign | Not Started
| CL-06 Admin listing management | Create/update/deactivate listing | Not Started
|  | Audit trail by user/time | Not Started
|  | Hide deactivated inventory from public | Not Started
| CL-07 Duplicate/stale flagging | Flag duplicate/stale records via admin rules | Not Started
|  | Review without auto-deletion | Not Started
| CL-08 Personalized discovery | Use searches, views, saves, location, budget, configuration, amenities | Not Started
|  | Apply consent/privacy controls | Not Started
| CL-09 Engagement metrics | Capture views and saves per listing | Not Started
|  | Apply agreed counting rules | Not Started
|  | Listing-level analytics | Not Started
B – GIS & Hyperlocal Intelligence | GIS-01 Geocoded location | Show property on base map | Not Started
| GIS-01 Geocoded location | Meet documented accuracy | Not Started
| GIS-02 Infrastructure/POI layers | ORR/RRR/metro/flyovers & amenity layers | Not Started
|  | Toggle layers | Not Started
|  | Source & last-updated metadata | Not Started
| GIS-03 Boundary overlays | Locality boundary overlays for launch geographies | Not Started
|  | Error-free geometry | Not Started
| GIS-04 Graceful API failure | Handle timeout/error without breaking property page | Not Started
|  | Monitor & expose error data to ops | Not Started
| GIS-05 Spatial dataset updates | Controlled dataset update | Not Started
|  | Record version & effective date | Not Started
|  | Rollback | Not Started
| GIS-06 Nearby updates | Detect new properties/developments/infra within approved radius | Not Started
|  | Show on dashboard & notification channels | Not Started
C – Kestimate | KE-01 Estimate request/view | Return estimate for supported types/areas | Not Started
| KE-01 Estimate request/view | Insufficient-data state; no fabricated values | Not Started
| KE-02 Range/confidence | Show range/confidence indicator | Not Started
|  | No single unexplained value | Not Started
| KE-03 Audit traceability | Store model version, timestamp, input features | Not Started
|  | Apply privacy controls | Not Started
| KE-04 Explainability | Show top value drivers/comparables in plain language | Not Started
| KE-05 Data-quality rules | Define thresholds for missing/stale/outlier inputs | Not Started
|  | Fallback behaviour | Not Started
|  | Log exceptions | Not Started
| KE-06 Monitoring | Track errors, latency, coverage, drift/quality | Not Started
|  | Segment by geography/property type | Not Started
| KE-07 Legal disclaimer | Show 'informational, not certified valuation' wherever displayed/shared | Not Started
| KE-08 GIS-driven refresh | Use infra/development/connectivity changes as inputs | Not Started
|  | Refresh current estimates & future projections | Not Started
D – Bujji AI Property Assistant | AI-01 Grounded answers | Answer from approved sources & user/property context | Not Started
| AI-01 Grounded answers | No invented facts | Not Started
| AI-02 Uncertainty & escalation | Indicate insufficient data | Not Started
|  | Bounded response; offer escalation | Not Started
| AI-03 Guardrails | Legal/financial disclaimers | Not Started
|  | Red-team/UAT verification | Not Started
| AI-04 Telemetry | Capture latency, failure, feedback, source IDs | Not Started
|  | Privacy-safe logs; ops can inspect failed/low-rated sessions | Not Started
| AI-05 Version control | Version prompt/model/config | Not Started
|  | Trace responses to deployed version | Not Started
| AI-06 Lead routing | Create lead/service request with consent | Not Started
|  | Include intent summary & property/project ID | Not Started
| AI-07 Memory/personalization | Retain preferences & prior context with consent | Not Started
|  | Avoid repeated questions | Not Started
E – K-Report & Legal Verification | KR-01 K-Report generation | Sections: property, ownership, registration, regulatory, location, risk/status | Not Started
| KR-01 K-Report generation | Mark missing evidence as unavailable/not verified | Not Started
| KR-02 Evidence tracking | Record source, date, verification status | Not Started
|  | Distinguish user-provided / system-fetched / professionally verified | Not Started
| KR-03 Legal-verification case | Create case with owner/partner, SLA, checklist | Not Started
|  | Track request → report delivery with timestamps | Not Started
| KR-04 Document access control | Restrict view/download to authorized roles | Not Started
|  | Log access | Not Started
| KR-05 Legal opinion separation | Label automated output as not legal opinion unless professionally signed | Not Started
| KR-06 Report versioning | Regenerate on source change | Not Started
|  | Keep prior versions; flag current | Not Started
F – MySecure | MS-01 Plan enrollment | Capture property, authorized contacts, plan, consent, special instructions | Not Started
| MS-01 Plan enrollment | Access/contact instructions | Not Started
| MS-02 Inspection scheduling | Schedule recurring visits per plan | Not Started
|  | Show upcoming/overdue with field owner | Not Started
| MS-03 Field inspection | Timestamped photos/video, checklist, notes | Not Started
|  | Block closure on incomplete checklist without exception reason | Not Started
| MS-04 Owner report & alerts | Post-inspection owner report | Not Started
|  | Critical-issue escalation | Not Started
| MS-05 Plan history & status | Maintain payments/service period | Not Started
|  | Active/expired/suspended state & renewal date | Not Started
| MS-06 Maintenance/vendor tasks | Track separately from inspection | Not Started
|  | Owner approval, cost, status | Not Started
| MS-07 Area alerts | Alerts on developments/infra/significant changes | Not Started
|  | Owner dashboard & notification channels | Not Started
G – KONU Buddies / Agent Network | KB-01 Buddy application | Capture identity, contact, coverage, experience, documents | Not Started
| KB-01 Buddy application | Block activation if verification incomplete | Not Started
| KB-02 Admin approval | Approve/reject/suspend with reason | Not Started
|  | Audit log; no leads to inactive/suspended | Not Started
| KB-03 Lead assignment | Assign owner, SLA, status, handoff notes | Not Started
|  | Track timestamps & next action | Not Started
| KB-04 Mandate/transaction workflow | Track property/customer & milestones | Not Started
|  | Audit changes; closed-lost reason | Not Started
| KB-05 Quality & feedback | Link metrics/feedback to Buddy profile | Not Started
|  | Performance reporting | Not Started
| KB-06 Commission policy | Configurable rule/reference recorded | Not Started
|  | No hardcoded rates; settlement out of scope | Not Started
| KB-07 Location-based matching | Match by location, service area, proximity, availability | Not Started
|  | Accept lead; single accountable owner; track status | Not Started
H – Developer Services, CRM & Growth Analytics | DEV-01 Developer/project onboarding | Capture company, project, RERA IDs, location, inventory, contacts | Not Started
| DEV-01 Developer/project onboarding | Admin verification before verified status | Not Started
| DEV-02 Project pages | Inventory/media/amenity/location content | Not Started
|  | Versioned, traceable to authorized source | Not Started
| DEV-03 Lead capture | Preserve project, channel/campaign, consent | Not Started
|  | Deduplicate per approved rules | Not Started
| DEV-04 Lead feedback loop | Sales/CRM status flows back | Not Started
|  | Report lead volume & downstream status | Not Started
| DEV-05 Funnel analytics | Document event taxonomy | Not Started
|  | QA acquisition → engagement → conversion events | Not Started
| DEV-06 Commercial model config | Configurable pricing/ACV/success-fee | Not Started
|  | No unapproved assumptions in logic | Not Started
| DEV-07 KONU Custom CRM | Customer, property, lead, Buddy, developer, transaction journeys | Not Started
|  | Unified history, integrations, reporting | Not Started
|  | Transition from third-party CRM | Not Started
I – Admin, Data Ops, Notifications & Platform Controls | ADM-01 Role-based access | Separate content, ops, QA, service, super-admin roles | Not Started
| ADM-01 Role-based access | Permission testing | Not Started
| ADM-02 Master data & exceptions | Manage master data, verification status, exception queues | Not Started
|  | Audited; no direct DB edits | Not Started
| ADM-03 Notification service | Transactional messages & delivery status | Not Started
|  | Log/retry failures | Not Started
| ADM-04 Pipeline status | Show last success, error, owner | Not Started
|  | Identify stale/failed sources | Not Started
| ADM-05 Audit trail | Actor/time/action history for critical entities | Not Started
| ADM-06 Environment separation | Separate dev/test/prod config | Not Started
|  | Isolate production secrets | Not Started
J – Customer Dashboard | CD-01 Property activity | Recently viewed | Not Started
| CD-01 Property activity | Saved/interested | Not Started
|  | Rejected/not-interested | Not Started
| CD-02 Analytics & insights | Customer-level property analytics | Not Started
|  | Insights from activity, preferences, owned properties | Not Started
| CD-03 New-match alerts | Alert on new property matching preferences | Not Started
|  | Card/notification with direct listing link | Not Started
| CD-04 Service status | Active KONU services incl. MySecure | Not Started
|  | Status, recent activity, next actions | Not Started
| CD-05 Personalized updates | Notifications & recommendations | Not Started
|  | Important journey updates | Not Started

## Data Science
Module | Task | Sub Task | Status
NFR – Platform Requirements | NFR-06 Analytics | Instrument funnel: discovery → lead/service request → fulfilment | Not Started
A – Core Listings, Search & Property Detail | CL-07 Duplicate/stale flagging | Flag duplicate/stale records via admin rules | Not Started
| CL-07 Duplicate/stale flagging | Review without auto-deletion | Not Started
| CL-08 Personalized discovery | Use searches, views, saves, location, budget, configuration, amenities | Not Started
|  | Apply consent/privacy controls | Not Started
| CL-09 Engagement metrics | Capture views and saves per listing | Not Started
|  | Apply agreed counting rules | Not Started
|  | Listing-level analytics | Not Started
B – GIS & Hyperlocal Intelligence | GIS-06 Nearby updates | Detect new properties/developments/infra within approved radius | Not Started
| GIS-06 Nearby updates | Show on dashboard & notification channels | Not Started
C – Kestimate | KE-01 Estimate request/view | Return estimate for supported types/areas | Not Started
| KE-01 Estimate request/view | Insufficient-data state; no fabricated values | Not Started
| KE-02 Range/confidence | Show range/confidence indicator | Not Started
|  | No single unexplained value | Not Started
| KE-03 Audit traceability | Store model version, timestamp, input features | Not Started
|  | Apply privacy controls | Not Started
| KE-04 Explainability | Show top value drivers/comparables in plain language | Not Started
| KE-05 Data-quality rules | Define thresholds for missing/stale/outlier inputs | Not Started
|  | Fallback behaviour | Not Started
|  | Log exceptions | Not Started
| KE-06 Monitoring | Track errors, latency, coverage, drift/quality | Not Started
|  | Segment by geography/property type | Not Started
| KE-07 Legal disclaimer | Show 'informational, not certified valuation' wherever displayed/shared | Not Started
| KE-08 GIS-driven refresh | Use infra/development/connectivity changes as inputs | Not Started
|  | Refresh current estimates & future projections | Not Started
D – Bujji AI Property Assistant | AI-01 Grounded answers | Answer from approved sources & user/property context | Not Started
| AI-01 Grounded answers | No invented facts | Not Started
| AI-02 Uncertainty & escalation | Indicate insufficient data | Not Started
|  | Bounded response; offer escalation | Not Started
| AI-03 Guardrails | Legal/financial disclaimers | Not Started
|  | Red-team/UAT verification | Not Started
| AI-04 Telemetry | Capture latency, failure, feedback, source IDs | Not Started
|  | Privacy-safe logs; ops can inspect failed/low-rated sessions | Not Started
| AI-05 Version control | Version prompt/model/config | Not Started
|  | Trace responses to deployed version | Not Started
| AI-06 Lead routing | Create lead/service request with consent | Not Started
|  | Include intent summary & property/project ID | Not Started
| AI-07 Memory/personalization | Retain preferences & prior context with consent | Not Started
|  | Avoid repeated questions | Not Started
G – KONU Buddies / Agent Network | KB-07 Location-based matching | Match by location, service area, proximity, availability | Not Started
| KB-07 Location-based matching | Accept lead; single accountable owner; track status | Not Started
H – Developer Services, CRM & Growth Analytics | DEV-05 Funnel analytics | Document event taxonomy | Not Started
| DEV-05 Funnel analytics | QA acquisition → engagement → conversion events | Not Started
I – Admin, Data Ops, Notifications & Platform Controls | ADM-04 Pipeline status | Show last success, error, owner | Not Started
| ADM-04 Pipeline status | Identify stale/failed sources | Not Started
J – Customer Dashboard | CD-02 Analytics & insights | Customer-level property analytics | Not Started
| CD-02 Analytics & insights | Insights from activity, preferences, owned properties | Not Started
| CD-03 New-match alerts | Alert on new property matching preferences | Not Started
|  | Card/notification with direct listing link | Not Started
| CD-05 Personalized updates | Notifications & recommendations | Not Started
|  | Important journey updates | Not Started